Professional Practice

30202191

Y/615/1620

Section (0)

Assignment Title

Planning a Training Event

Assignment 1 – Part 1

GROUP WORK

Submitted to

Nora Alnashef

Submitted by

Khaled Shadi Alkholi (Team Leader)

Abdallah Nabil Mesleh

Omar Majdi Abdo

Omar Eyad AbedKhader

Osama Salah-Eldeen Qujaq

Spring 2021 - 2022

Table of Content

Part 1...........................................................................................................................................

References...................................................................................................................................

Part 2...........................................................................................................................................

References...................................................................................................................................

Part 3...........................................................................................................................................

References...................................................................................................................................

The aim of this report is to discuss our plan for the 2-day orientation event that will be held in Al-Hussein Technical University at the end of September 2023. The Computing and Informatics Department in HTU holds an orientation event every year for the new students. We, The Professional Squad, were given a 2-month preparation period to plan for this event and gather all the resources needed.

The orientation event will be carried out in the university, and it’ll mainly include the following:

- Welcoming session: This session will be about greeting the new students to HTU.

- Introduction to HTU educational environment: As the educational environment in HTU isn’t as same as other universities, most students won’t be familiar with it, so this introduction will give them a good understanding of how the whole academic system works in HTU.

- A brief about opportunities in HTU: Htu provides good opportunities regarding students’ careers and internships. So, it’s important to clearly explain to new students how to take advantage of those opportunities to build their bright future.

- Introducing students to their fields of study: This part helps student decide and choose the best major that they find themselves comfortable with.

- A small trip around HTU faculties: It’s good to give new students a walk around HTU faculties so that they get more comfortable and familiar with the university in general.

In addition, this report will explain how we managed our time and how the roles were distributed between us and how we dealt with limitations we faced in the process of planning this event. Also, a time schedule will be provided as well. This time schedule demonstrated exactly how much time we have given to each task in either the preparation period or in the 2-day orientation event period.

Part One:

-Intro to the event (about 300 words) (activities and workshops)

-Professional schedule

- contingencies, (plan b’s)

-orientation pack

Professional Practice

30202191

Y/615/1620

Section (0)

Assignment Title

Planning a Training Event

Assignment 1 – Part 1

INDIVIDUAL WORK

Submitted to

Instructor Name

Submitted by

Student Name

Spring 2021 - 2022

Contents

Part1............................................................................................................................................

References...................................................................................................................................

Part 2...........................................................................................................................................

References...................................................................................................................................

Part 3...........................................................................................................................................

References...................................................................................................................................

Guidelines

Font type: Times new Romans (أبجد هوز)

Font size: 12

Spacing: 1.0

Font colour: Black

Bold Fonts: Only for headings

Pages should be numbered

Word document not pdf

No zip files when uploading to e-learning